## Trisha Espejo
To-do list
To be completed by: |  |  |  | Trisha Espejo
Deadline: |  |  |  | 2020-10-25
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-10-17 | 2020-10-17
100% | Preparation | 2020-10-17 | 2020-10-17
100% | Finish Easy Queries | 2020-10-16 | 2020-10-17 | 2020-10-23 |  | resloved: the easy queson is too easy and needs to be 2 table join
100% | Finish Medium Queries | 2020-10-18 | 2020-10-19 | 2020-10-22 |  | resolved: need group by clause
100% | Finish Hard Queries | 2020-10-19 | 2020-10-23 | 2020-10-20 |  | resolved: needs to add scalar function
100% | JBDC | 2020-10-20 | 2020-10-23 | 2020-10-22 |  | resolved: problem with loading queries
100% | Paperwork | 2020-10-21 | 2020-10-23 | 2020-10-23 |  | resolved:powerpoint in mp4 format
100% | Hand-off | 2020-10-22
100% | Follow-up | 2020-10-17 |  |  |  | resolved: comprehend project role and inquire help on jdbc